## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 8 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [6 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Topic Selection | 1 | 1 | 1 | 1 | 100% | [27 empty] | Note: This Gantt chart is for actual research proposal, not for ANN example..As this was optional submission, I went ahead with the actal one..I don’t know who will check this, but if you are doing, please leave comments if any improvements are needed. Thanks..
Milestone 1 : Topic Submission | 1 | 1 | 1 | 1 | 100%
Literature Review | 2 | 3 | 2 | 4 | 100%
Research Planning | 4 | 2 | 4 | 2 | 100%
Prepare research proposal | 5 | 2 | 5 | 2 | 100%
Milestone 2 : Research proposal submission | 7 | 1 | 7 | 1 | 100%
Literature Review | 7 | 3 | 7 | 2 | 70%
Data Preparation | 9 | 1 | 0 | 0 | 0%
Data Processing | 9 | 2 | 0 | 0 | 0%
EDA | 10 | 2 | 0 | 0 | 0%
Preparing Interim report | 12 | 3 | 0 | 0 | 0%
Milestone 3 : Interim Report Submission | 15 | 1 | 0 | 0 | 0%
Model Building and Model Evaluation | 16 | 4 | 0 | 0 | 0%
Model Comparing and Analysis | 18 | 2 | 0 | 0 | 0%
Compile Learnings | 20 | 2 | 0 | 0 | 0%
Conclusion | 22 | 1 | 0 | 0 | 0%
Preparing Final Report | 23 | 2 | 0 | 0 | 0%
Preparing Final Report Video Presentation | 24 | 2 | 0 | 0 | 0%
Milestone 4 : Final Report Submission | 26 | 1 | 0 | 0 | 0%